## RMS
Screen/Function | Description | Level | LOC | Planned-In | In Charge | Done-In | RDS | Status | Updated | Update Details
Home Page | [Names of use cases (UCs) and brief description for each UC in the form of "As a <type of user>, I want <some goal> so that <some reasons>" or in other form that we can have overall understanding of the UC] | Level 3 | 120 | Iteration 1 | HuyTQ | Iteration 1 | II.1.3, III.5 | To Do | Not Yet
Manage Packages | 1. Manage Packages: As an admin, I want to create, update, and delete swimming packages so that users can choose suitable options for booking. | Level 3 | 120 | Iteration 1 | Du | Iteration 1 |  | To Do | Not Yet
User profile | 1. View & Update Profile: As a user, I want to view and edit my personal profile information so that my account stays up to date and accurate. | Level 3 | 120 | Iteration 1 | Du | Iteration 1 |  | To Do | Not Yet
User Login | 1. Login System: As a user with a specific role, I want to be redirected to the appropriate page after login so that I can immediately access the features relevant to my role | Level 2 | 90 | Iteration 1 | Huynv | Iteration 1 | II.2.1; III.1.1.a | To Do | Not Yet
User Register | 1. Register User Account: As a new user, I want to register an account with my full name, email and password so that I can access the features of the system | Level 3 | 120 | Iteration 1 | Huynv | Iteration 1 |  | To Do | Not Yet
Notification System (basic) | As a user, I want to receive timely notifications about my bookings, updates, or changes so that I can stay informed. | Level 2 | 90 | Iteration 1 | XumLM | Iteration 1 |  | To Do | Not Yet
Password Reset | 1. Reset Password: As a registered user, I want to request a password reset by entering my email so that I can regain access to my account if I forget my password | Level 2 | 90 | Iteration 1 | XumLM | Iteration 1 |  | To Do | Iteration 2
Manage Roles | 1. Manage Roles: As an admin, I want to assign and manage user roles so that I can control access to different features in the system. | Level 3 | 120 | Iteration 1 | ThuongNQ | Iteration 1 |  | To Do | Not Yet
Employee profile | Manages the entire swimming pool facility, ensuring smooth daily operations. Responsible for coordinating staff, maintaining water quality, managing pool schedules, and ensuring that all safety and hygiene standards are met. | Level 3 | 120 | Iteration 1 | HuyTQ | Iteration 1 |  | To Do | Not Yet
Swimming pool profile | Create and manage detailed information of each swimming pool in the system, serving to display publicly to customers, as well as supporting internal operations, maintenance, and quality monitoring. | Level 3 | 120 | Iteration 1 | ThuongNQ | Iteration 1 |  | To Do | Not Yet
User reviews | Allows users to write reviews, rate, and view other people's reviews of an entity (product, service, article, user, etc.). | Level 2 | 90 | Iteration 1 | XumLM | Iteration 1 |  | To Do | Not Yet
Event detail | View and manage the full information of a scheduled event. This includes the event name, date & time, location, assigned staff, number of participants, and any special notes or requirements. | Level 2 | 90 | Iteration 1 | Huynv | Iteration 1 |  | To Do | Not Yet
Payment Manager | The Payment Manager feature enables administrators to monitor, process, and manage all payment-related activities within the system. It provides a centralized interface to track transactions, handle refunds, verify payment statuses, and generate financial reports. | Level 6 | 210 | Iteration 2 | XumLM | Iteration 2 |  | To Do | Not Yet
Book Swimming Trainer | 1. Booking: As a user, I want to book a lesson with a trainer. | Level 5 | 180 | Iteration 2 | HuyTQ | Iteration 2 |  | To Do | Not Yet
Manger Schedules | The Manage Schedules feature allows administrators to create, view, update, and delete scheduled tasks, events, or activities within the system. This feature helps ensure efficient time management, resource planning, and coordination among users or departments. | Level 6 | 210 | Iteration 2 | Huynv | Iteration 2 |  | To Do | Not Yet
Dash Board (User) | The User Dashboard is a personalized interface where users can view and manage their account information, track orders or activities, access services, and receive important updates or notifications. | Level 6 | 210 | Iteration 2 | ThuongNQ | Iteration 2 |  | To Do | Not Yet
View Report(Admin) | The View Report feature in the Admin Dashboard allows administrators to access detailed reports on system activities, user behavior, sales, performance metrics, and other key data. These reports help in monitoring trends, identifying issues, and making data-driven decisions. | Level 5 | 180 | Iteration 2 | Du | Iteration 2 |  | To Do | Not Yet
Dash Board (Admin) | The Admin Dashboard is the central interface that allows administrators to monitor system performance, manage users, content, orders, and view important notifications quickly and efficiently. | Level 6 | 210 | Iteration 2 | Du | Iteration 2 |  | To Do | Not Yet
Change password | As a user, I want to change my password so that I can keep my account secure. | Level 3 | 120 | Iteration 2 | HuyTQ | Iteration 3 |  | To Do | Not Yet
event management | Allows admins or authorized users to create, update, manage and track events held at the pool; and allows customers to register, receive notifications, and track details of each event. | Level 5 | 180 | Iteration 2 | XumLM | Iteration 4 |  | To Do | Not Yet
Blog Page | As a user, I want to view and manage blog posts so that I can share and organize my content effectively. | Level 5 | 180 | Iteration 3 | XumLM | Iteration 3 |  | To Do | Not Yet
Update Profile | As a user, I want to update my personal information so that my profile reflects accurate and current details. | Level 4 | 150 | Iteration 3 | Du | Iteration 3 |  | To Do | Not Yet
Swim history | As a user, I want to view my swimming history so that I can track my progress and activity over time | Level 5 | 180 | Iteration 3 | HuyTQ | Iteration 3 |  | To Do | Not Yet
Employee schedule list | Provides administrators or coaches the ability to track and manage work schedules and teaching schedules of coaches at the pool. | Level 6 | 210 | Iteration 3 | Du | Iteration 3 |  | To Do | Not Yet
Send advanced notifications | ..Send automated or scheduled notifications to clients, trainers or staff about events, reminders, schedule changes, promotions, emergency information | Level 5 | 180 | Iteration 3 | Huynv | Iteration 3 |  | To Do | Not Yet
Payment details | ..Provide users and administrators with the ability to view, track and manage detailed information about payment transactions related to the use of services at the pool such as: swimming package purchases, swimming class tuition, coach rentals, ancillary services | Level 6 | 210 | Iteration 3 | Huynv | Iteration 3 |  | To Do | Not Yet
swimming facility management | Support the management board to monitor, update usage status, maintenance schedule and manage assets related to swimming pools such as swimming pools, changing rooms, lockers, water filtration equipment, seats, lighting systems, sensors, buoys, lifeguards... | Level 6 | 210 | Iteration 3 | ThuongNQ | Iteration 3 |  | To Do | Not Yet
warehouse manager | ..Show users a confirmation page after completing a key action like a successful payment, VIP membership signup, important swim lesson booking, or event registration. This page helps create a sense of certainty, security, and professionalism. | Level 6 | 210 | Iteration 3 | ThuongNQ | Iteration 3 |  | To Do | Not Yet
Employee management | Manage employee profiles, roles, work schedules, and responsibilities. You can add, edit, or deactivate staff accounts and assign them specific permissions or tasks. | Level 5 | 180 | Iteration 3 | ThuongNQ | Iteration 3 |  | To Do | Not Yet
Service management | A Service Management System (SMS) is designed to help organizations plan, deliver, monitor, and improve services provided to customers | Level 5 | 180 | Iteration 3 | Du | Iteration 3 |  | To Do | Not Yet
Users management | Manage customer or user accounts who use your swimming pool services. Track their usage history, membership status, bookings, and feedback. | Level 5 | 180 | Iteration 3 | XumLM | Iteration 3 |  | To Do | Not Yet
Dash Board (Employee ) | Manage customer or user accounts who use your swimming pool services. Track their usage history, membership status, bookings, and feedback. | Level 5 | 180 | Iteration 3 | XumLM | Iteration 3 |  | To Do | Not Yet

## Params
Screen/Function Complexity Levels
Screen complexity can be defined based on the screen's fields OR screen/function's transactions | Level | Fields | Trans* | LOC | Notes
- Transactions can be counted as number of transactions to the database or external systems/subsystems | Level 1 | 3-5 | 2 | 60 | 3-5 fields and 2 trans
- Fields are screen's actionable components or database table fields; if there are some transactions those are | Level 2 | 6-7 | 3 | 90 | 6-7 fields and 3 trans
not "related" to any fields, each of those transactions are counted as two fields and add those extra number | Level 3 | 8-9 | 4 | 120 | 8-9 fields and 4 trans
to the total number of fields to define the screen/function complexity | Level 4 | 10-11 | 5 | 150 | 10-11 fields and 5 trans
| Level 5 | 12-13 | 6 | 180 | 12-13 fields and 6 trans
Some samples of screen complexity defining are as following | Level 6 | 14-15 | 7 | 210 | 14-15 fields and 7 trans
Sample #1 | Level 7 | >15 | >7 | 240 | >15 fields and >7 trans
*One trans (transactions) = Two fields (actionable screen components)
Sample #2
Sample #3